## Sheet1
Test Cases for Gradific Web Application
Tested By: Isioma Ogbechie |  |  | TEST STATUS | TEST SUMMARY |  | PRIORITY
Date: 21/10/2025 |  |  | Pass | 7 |  | High | 13
Project: Gradific Web App |  |  | Fail | 2 |  | Medium | 1
Test Environment: Staging / Web |  |  | Not Excuted (NE) | 5 |  | Low | 0
|  |  | Not Applicable (NA) | 0 |  | TOTAL | 14
|  |  | TOTAL | 14
Testcase ID | Module | Test Description | Precondition | Test Steps | Expected Result | Actual Result | Priority | Status
TC_001 | User Onboarding | Verify that a new user can sign up successfully with valid details | User on registration page | 1. Launch the url 2. Click on Create Account 3. Enter valid credential on the Sign Up page 4. Click on Sign Up button | User should be able to Sign up sucessfully with valid credentials | User was able to Sign up successfully | High | Pass
TC_002 |  | Verify that user cannot Sign Up with empty fields | User on registration page | 1. Launch the url 2. Click on Create Account 3. Leave all fields empty 4. Click on Sign Up button | A validation message should be displayed, prompting the user to fill required fields. | A validation message was displayed prompting the user to fill all required field | High | Pass
TC_003 |  | Verify that user cannot Sign Up with invalid email and a valid password | User on registration page | 1. Launch the url 2. Click on Create Account 3. Enter an invalid email: oganaisioma@gmail.co 4. Enter other fields correctly 5. Click on Sign Up button | A validation message should be displayed prompting the user to enter a valid email | User was able to Sign Up sucessfully. No validation message was displayed | High | Fail
TC_004 |  | Verify user cannot Sign up with mismatched passwords | User on registration page | 1. Launch the url 2. Click on Create Account 3. Enter a valid email: oganaisioma@gmail.com 4. Enter password :Stepha@ine_5560 5. Enter a different password in the Confirm Password field: ogbechieiss_y78 6. Click on Sign Up button | An error message should be displayed prompting the user to enter matching passwords | An error message was displayed showing, "Passwords must match!" | High | Pass
TC_005 | Authentication | Verify login with valid credentials | - User account exists. - User is on the Login page. | 1. Enter valid email and password 2. Click Log in button | User should be logged in successfully and redirected to dashboard | User was logged in successfully and redirected to dashboard. | High | Pass
TC_006 |  | Verify login with invalid credentials | - User account exists. - User is on the Login page. | 1. Enter wrong email/password 2. Click Log in | An error message should be displayed prompting the user to enter valid credentials | An error message was displayed prompting the user to enter valid credentials | High | Pass
TC_007 |  | Verify login with empty fields | - User account exists. - User is on the Login page. | 1. Leave Email and Password field empty 2. Click Log in | An error message should be displayed prompting the user to enter email and password | An error message was displayed, showing "Email and Password is required". | High | Pass
TC_008 | Workspace | Verify that user can create a workspace | User is on the workspace dashboard | 1. Log in 2. Click on Create a New Workspace | User should be able to create a new workspace | User was able to create a new workspace | High | Pass
TC_009 |  | Verify that user can create more than one workspace | User is on the workspace dashboard | 1. Log in 2. After creating a new work space,click on Create a New Workspace to create another workspace | User should be able to create more than one workspace | User was not able to create another workspace | Medium | Fail
TC_010 | Assignment Creation | Verify that Owner can create an assignment successfully | User logged in as Owner and created a workspace | 1.Navigate to Assignments dashboard 2. Click on Create New 3. Fill all fields 4. Save | - Owner should be able to create assignment successfully - Assignment should be visible on dashboard |  | High | NE
TC_011 |  | Verify that assignment cannot be created with missing fields | User logged in as Owner and created a workspace | 1.Navigate to Assignments dashboard 2. Click on Create New 3. Leave title blank 3. Fill other fields 4. Save | An error message should be displayed, showing “Title is required” displayed" |  | High | NE
TC_012 | Assignment Submission | Verify member can submit assignment before deadline | Member assigned task | 1.Navigate to Assignments dashboard 2. Click on Create New 3.Fill other fields 4. Set deadline date using date picker 5. Save | “Submission successful” message should be displayed |  | High | NE
TC_013 |  | Verify system rejects submission after deadline | Deadline passed | 1. Atrtempt submitting task | Error “Deadline has passed” should be displayed |  | High | NE
TC_014 |  | Verify system prevents empty submission | Member assigned task | 1. Click Submit without attaching file | A validation message should be displayed, showing: “File required” |  | High | NE